## Custom CRM
Phase | Tasks | Time Estimate
Phase 1: Planning & Design | Finalizing requirements, designing database schema & architecture | 2 weeks
Phase 2: Backend Development | Building APIs (CRM, order tracking, contracts, invoices) | 6-8 weeks
Phase 3: Frontend Development | Customer & Admin dashboard with tracking, reports, and user access | 6-8 weeks
Phase 4: Integrations | Connecting WMS, TMS, payment gateways, notifications | 4-6 weeks
Phase 5: Testing & Security | API testing, role-based access, stress testing | 3-4 weeks
Phase 6: Deployment & Training | Launching on cloud, providing client training | 2 weeks
Total Development Time | 4-6 months (MVP in 3-4 months)
MVP - Prioritize features will be released earlier and ongoing updates
Techonlogy Stack -- Django

## Details of the Phases
3PL CRM Development Roadmap
Estimated Time: 4-6 months (MVP in 3-4 months)
Recommended Team: Backend Developer, Frontend Developer, UI/UX Designer
Phase 1: Planning & System Design (Week 1-2)
Milestones
| 1 | Finalize tech stack (Django vs Node.js, PostgreSQL vs MongoDB)
| 2 | Define user roles (Admin, Customer, Carrier, Sales, Finance)
| 3 | Design database schema (Customer, Orders, Contracts, Billing, Shipment, SLA)
| 4 | Create API architecture (REST/GraphQL)
| 5 | Plan integrations (WMS, TMS, Payment, Notifications)
Deliverables
| 1 | System architecture diagram
| 2 | ERD (Entity-Relationship Diagram) for database
| 3 | API documentation draft
Phase 2: Backend Development (Week 3-10)
Milestones
| 1 | Set up the backend framework (Django REST Framework / Node.js with Express)
| 2 | Implement authentication (JWT, OAuth, Role-Based Access Control)
| 3 | Develop core CRM modules:
Customer Management
| 1 | Profile
| 2 | Contracts
| 3 | Communication History
Lead & Opportunity Tracking
| 1 | Sales funnel
| 2 | Quotes
| 3 | Revenue Projection
Order & Shipment Tracking (Real-time updates via WMS/TMS)
| 1 | Automate invoice & contract management
| 2 | Set up background tasks (Celery for Python, BullMQ for Node.js)
Deliverables
| 1 | API endpoints for CRM, orders, and tracking
| 2 | Secure authentication system
| 3 | Automated invoicing and reminders
Phase 3: Frontend Development (Week 6-12)
Milestones
| 1 | Set up frontend framework
| 2 | Implement user authentication (Login, Signup, Role-based UI)
| 3 | Create dashboards
Admin Panel (Order & Customer Management, Analytics)
Customer Portal (Order tracking, Invoice download)
B2B Portal (Shipment planning, Carrier Slot Booking)
| 4 | Implement interactive features (Notifications, Reports, Graphs)
Deliverables
| 1 | Responsive UI for CRM Dashboard
| 2 | Customer & Admin portals with live tracking
| 3 | Role-based navigation
Phase 4: Integrations (Week 10-16)
Milestones
| 1 | Connect CRM with WMS & TMS for real-time updates
| 2 | Integrate shipment tracking APIs (DHL, FedEx, UPS, etc.)
| 3 | Implement payment gateways (razorpay) for invoicing
| 4 | Set up email & WhatsApp notifications
Deliverables
| 1 | Working integrations for shipment tracking
| 2 | Automated payment processing
| 3 | Real-time notification system
Phase 5: Testing & Security (Week 14-18)
Milestones
| 1 | Unit testing for backend APIs
| 2 | Security testing (SQL Injection, CSRF, XSS Protection)
| 3 | Performance testing (Handling 10k+ orders)
| 4 | User acceptance testing (Client feedback)
Deliverables
| 1 | Secure & optimized CRM system
| 2 | Test reports with bug fixes
Phase 6: Deployment & Training (Week 18-20)
Milestones
| 1 | Deploy on VPS with Docker & Nginx
| 2 | Provide client training & documentation
| 3 | Collect feedback for future updates
Deliverables
| 1 | Live CRM on production
| 2 | Training materials & user guide